## WBS
Function/Screen | Feature | Sub Feature | Type | Function/Screen Description | Level* | Est. Effort | Planned | Status | SRS | In-Charge | Deadline | IT Case | In-Charge | Deadline | IT Case | In-Charge | Deadline | Notes
UC-01 View replenishment request list | FE-01 | Purchase / Receipt | Screen | Sales and Warehouse Staff view their own/assigned replenishment needs; Owner and Accountant view within responsibility and warehouse scope. | Simple | 0.25 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W9; code 06/11/2026
UC-02 View replenishment request details | FE-01 | Purchase / Receipt | Screen | Show requested and available quantities, source demand, pending supply allocations and versioned approval history within authorized scope. | Simple | 0.25 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W9; code 06/11/2026
UC-03 Create replenishment request | FE-01 | Purchase / Receipt | Screen | Sales Staff raises customer shortages; Warehouse Staff raises stock needs after checking compatible stock, existing PO/transfer supply and minimum levels. Accountant does not originate operational demand. | Medium | 1 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W9; code 06/11/2026
UC-04 Approve or reject replenishment request | FE-01 | Purchase / Receipt | Screen | Store Owner approves, rejects or returns the exact request version for revision. Requester and approver must be different userIds; no PO before approval. | Medium | 1 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W9; code 06/11/2026
UC-05 View purchase order list | FE-01 | Purchase / Receipt | Screen | Filter orders by supplier, date, status, and outstanding quantity. | Simple | 0.25 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W9; code 06/11/2026
UC-06 View purchase order details | FE-01 | Purchase / Receipt | Screen | Display order lines, supplier confirmations, and partial receipt history. Display ordered, confirmed, received, accepted and outstanding quantities with source receipts. This is read-only, not a separate outstanding-quantity UC. | Simple | 0.25 | Iteration 2 | Planned | To Do | minhtd | 13/11/26 | To Do | hieudt | 18/11/26 | To Do | hieudt | 20/11/26 | minhtd; W10; code 13/11/2026
UC-07 Manage Purchase Order and Supplier Confirmation | FE-01 | Purchase / Receipt | Screen | Accountant creates a PO against approved replenishment lines, records supplier confirmation and tracks partial receipts. Changes beyond approval require reapproval; no supplier payment. | Medium | 1 | Iteration 2 | Planned | To Do | minhtd | 13/11/26 | To Do | hieudt | 18/11/26 | To Do | hieudt | 20/11/26 | minhtd; W10; code 13/11/2026
UC-08 View goods receipt list | FE-01 | Purchase / Receipt | Screen | Search deliveries associated with purchase orders and their processing status. | Simple | 0.25 | Iteration 2 | Planned | To Do | minhtd | 13/11/26 | To Do | hieudt | 18/11/26 | To Do | hieudt | 20/11/26 | minhtd; W10; code 13/11/2026
UC-09 View goods receipt details | FE-01 | Purchase / Receipt | Screen | Display delivered, accepted, pending inspection, defective, and rejected quantities. | Simple | 0.25 | Iteration 2 | Planned | To Do | minhtd | 13/11/26 | To Do | hieudt | 18/11/26 | To Do | hieudt | 20/11/26 | minhtd; W10; code 13/11/2026
UC-10 Create goods receipt from purchase order | FE-01 | Purchase / Receipt | Screen | Warehouse Staff records each delivery against PO lines, including actual quantities, discrepancies and evidence; creating the draft does not post inventory. | Medium | 1 | Iteration 2 | Planned | To Do | minhtd | 13/11/26 | To Do | hieudt | 18/11/26 | To Do | hieudt | 20/11/26 | minhtd; W10; code 13/11/2026
UC-11 View product list | FE-02 | Purchase / Receipt | Screen | Search products by item code, name, size, and status. | Simple | 0.25 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W8; code 30/10/2026
UC-12 View product details | FE-02 | Purchase / Receipt | Screen | Display tile attributes, packaging specifications, and units of measure. | Simple | 0.25 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W8; code 30/10/2026
UC-13 Maintain Product and Packaging | FE-02 | Purchase / Receipt | Screen | Maintain versioned BOX/PIECE/M2 conversions and controlled minimum stock parameters. Preserve transaction snapshots; count remaining pieces in open boxes. Torn packaging alone does not mean damaged tiles. | Medium | 1 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W8; code 30/10/2026
UC-14 View lot list | FE-02 | Purchase / Receipt | Screen | Search lots by product, lot number, tone, and actual calibre. | Simple | 0.25 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W8; code 30/10/2026
UC-15 View lot details | FE-02 | Purchase / Receipt | Screen | Display production date, tone, actual calibre, and related transaction history. | Simple | 0.25 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W8; code 30/10/2026
UC-16 Maintain Product Lot | FE-02 | Purchase / Receipt | Screen | Maintain product/lot/tone/actual-calibre identity with evidence and history. Do not overwrite transacted identity to conceal shortages. Survey size is not proof of actual-calibre tracking. | Medium | 1 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W8; code 30/10/2026
UC-17 View supplier list | FE-02 | Purchase / Receipt | Screen | Search suppliers by code, name, and cooperation status. | Simple | 0.25 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W8; code 30/10/2026
UC-18 View supplier details | FE-02 | Purchase / Receipt | Screen | Display contact information and related purchases, receipts, and returns. | Simple | 0.25 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W8; code 30/10/2026
UC-19 Maintain Supplier | FE-02 | Purchase / Receipt | Screen | Maintain supplier identity/contact data and control supplier availability with separate operation permissions. | Medium | 0.75 | Iteration 1 | Planned | To Do | minhtd | 30/10/26 | To Do | hieudt | 04/11/26 | To Do | hieudt | 06/11/26 | minhtd; W9; code 06/11/2026
UC-20 View Customer List | FE-02 | Customer master | Screen | Search delivery/contact references and external MISA customer identifiers within authorized scope; no CRM or commercial account ledger. | Simple | 0.25 | Iteration 1 | Planned | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | bachhm; W8; code 30/10/2026
UC-21 View Customer Details | FE-02 | Customer master | Screen | Read customer delivery/contact and source-document references; no sales pricing or receivables. | Simple | 0.25 | Iteration 1 | Planned | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | bachhm; W8; code 30/10/2026
UC-22 Maintain Customer | FE-02 | Customer master | Screen | Sales Staff maintains basic customer delivery/contact data and external identifiers; no commercial sales or CRM workflow. | Medium | 0.75 | Iteration 1 | Planned | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | bachhm; W8; code 30/10/2026
UC-26 Inspect and Post Goods Receipt | FE-03 | Purchase / Receipt | Screen | Warehouse Staff inspects each delivered quantity and posts only accepted ownership by quality/location once. Owner/Accountant may assist physically and be recorded in evidence; they do not inherit GR posting rights. Custody is separate; torn packaging alone is not damage. | Complex | 1.5 | Iteration 2 | Planned | To Do | minhtd | 13/11/26 | To Do | hieudt | 18/11/26 | To Do | hieudt | 20/11/26 | minhtd; W11; code 20/11/2026
UC-27 View warehouse and location list | FE-04 | Movement / Transfer | Screen | Search by warehouse, area, aisle, rack, and location code. | Simple | 0.25 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W8; code 30/10/2026
UC-28 View storage location details | FE-04 | Movement / Transfer | Screen | Display capacity, status, and lot-level quantities at a location. | Simple | 0.25 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W8; code 30/10/2026
UC-29 Maintain Storage Location | FE-04 | Movement / Transfer | Screen | Create, update or deactivate storage locations. | Medium | 0.75 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W8; code 30/10/2026
UC-30 View stock by lot, location, and quality status | FE-04 | Movement / Transfer | Screen | Show stock by warehouse/location/lot/quality/ownership, with reserved, available and in-transit quantities separated and restricted by data scope. | Simple | 0.25 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W8; code 30/10/2026
UC-31 View inventory balance details | FE-04 | Movement / Transfer | Screen | Display physical, usable, reserved, available, custody and transit balances with source movements; do not double count staging/reservations. | Simple | 0.25 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W8; code 30/10/2026
UC-32 Create Put-away Task | FE-04 | Purchase / Receipt | Screen | Create or accept a suggested internal put-away task from a posted receipt; no second receiving or approval document. | Medium | 0.75 | Iteration 2 | Planned | To Do | minhtd | 13/11/26 | To Do | hieudt | 18/11/26 | To Do | hieudt | 20/11/26 | minhtd; W11; code 20/11/2026
UC-33 Confirm Put-away Task | FE-04 | Purchase / Receipt | Screen | Warehouse Staff confirms actual placement, preserving total owned quantity and quality. Make accepted stock allocatable only in a suitable location. | Medium | 1 | Iteration 2 | Planned | To Do | minhtd | 13/11/26 | To Do | hieudt | 18/11/26 | To Do | hieudt | 20/11/26 | minhtd; W11; code 20/11/2026
UC-34 View location movement list | FE-04 | Movement / Transfer | Screen | Search same-warehouse movements by lot and status. | Simple | 0.25 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W8; code 30/10/2026
UC-35 View location movement details | FE-04 | Movement / Transfer | Screen | Display source, destination, and actual transferred quantities. | Simple | 0.25 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W8; code 30/10/2026
UC-36 Create location movement | FE-04 | Movement / Transfer | Screen | Warehouse Staff selects compatible source/destination locations in the same warehouse and checks quantity, reservations and stocktake locks; no Owner approval or inter-warehouse TR. | Medium | 1 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W9; code 06/11/2026
UC-37 Confirm actual location movement | FE-04 | Movement / Transfer | Screen | Confirm actual relocation atomically: source minus q, destination plus q, same lot/quality/owner and total. Carry reservations and block locked locations. | Complex | 1.5 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W9; code 06/11/2026
UC-38 View warehouse transfer list | FE-05 | Movement / Transfer | Screen | View transfers between the configured warehouses; D4 confirms inter-warehouse movements. Sales sees progress related to its issue requests. | Simple | 0.25 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W9; code 06/11/2026
UC-39 View warehouse transfer details | FE-05 | Movement / Transfer | Screen | Show requested/approved, dispatched, received by quality, in-transit and unresolved quantities with separate dispatch and receipt documents. | Simple | 0.25 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W9; code 06/11/2026
UC-40 Create Transfer Request | FE-05 | Movement / Transfer | Screen | Warehouse Staff requests physical movement between distinct warehouses after considering direct customer dispatch or other compatible sources. Same-warehouse relocation uses UC-36/37. | Medium | 1 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W9; code 06/11/2026
UC-41 Review Transfer Request | FE-05 | Movement / Transfer | Screen | Store Owner approves/rejects/returns the TR version; requester differs from approver. Approved TR authorizes execution and controlled source reservation; no extra inter-warehouse TO approval. | Medium | 1 | Iteration 2 | Planned | To Do | hieudt | 13/11/26 | To Do | bachhm | 18/11/26 | To Do | bachhm | 20/11/26 | hieudt; W10; code 13/11/2026
UC-43 Record Transfer Dispatch | FE-05 | Movement / Transfer | Screen | Warehouse drafts TD from approved TR before picking; confirms actual picking TO when staging applies, then posts TD/HO only at handover. No second GI or Owner task approval. | Complex | 1.5 | Iteration 2 | Planned | To Do | hieudt | 13/11/26 | To Do | bachhm | 18/11/26 | To Do | bachhm | 20/11/26 | hieudt; W10; code 13/11/2026
UC-44 Review Transfer Difference Resolution | FE-05 | Movement / Transfer | Screen | Store Owner reviews inter-warehouse discrepancies from UC-43/104. Resolve through linked documents without editing posted quantities; keep unmatched amounts open. | Medium | 1 | Iteration 2 | Planned | To Do | hieudt | 13/11/26 | To Do | bachhm | 18/11/26 | To Do | bachhm | 20/11/26 | hieudt; W10; code 13/11/2026
UC-45 View Copied Sales Order List | FE-06 | Sales / Issue | Screen | Read scoped SO source, customer, issued/delivered/outstanding quantities and DELIVERED/COMPLETED progress. | Simple | 0.25 | Iteration 1 | Planned | To Do | danghh | 30/10/26 | To Do | minhtd | 04/11/26 | To Do | minhtd | 06/11/26 | danghh; W8; code 30/10/2026
UC-46 View Copied Sales Order Details | FE-06 | Sales / Issue | Screen | Read copied source lines, WIR/OD/GI/POD/PAY-CFM history and cancellations; no pricing, invoice or payment calculation. | Simple | 0.25 | Iteration 1 | Planned | To Do | danghh | 30/10/26 | To Do | minhtd | 04/11/26 | To Do | minhtd | 06/11/26 | danghh; W8; code 30/10/2026
UC-47 Create Copied Sales Order | FE-06 | Sales / Issue | Screen | Sales manually copies a verified external order with source line identity and evidence. Reject duplicate source orders/lines; entry changes no stock. | Medium | 1 | Iteration 1 | Planned | To Do | danghh | 30/10/26 | To Do | minhtd | 04/11/26 | To Do | minhtd | 06/11/26 | danghh; W8; code 30/10/2026
UC-48 Update or Cancel Unissued Sales Order Remainder | FE-06 | Sales / Issue | Screen | Sales changes only unexecuted or posted-GR-FD-received-back, not-redelivered quantity on the original SO. Preserve source and gross ledger; unresolved off-site stock cannot be cancelled. | Medium | 1 | Iteration 1 | Planned | To Do | danghh | 30/10/26 | To Do | minhtd | 04/11/26 | To Do | minhtd | 06/11/26 | danghh; W8; code 30/10/2026
UC-49 View Outbound Delivery List | FE-06 | Sales / Issue | Screen | Read-only outbound delivery search and listing. | Simple | 0.25 | Iteration 1 | Planned | To Do | danghh | 30/10/26 | To Do | minhtd | 04/11/26 | To Do | minhtd | 06/11/26 | danghh; W8; code 30/10/2026
UC-50 View Outbound Delivery Details | FE-06 | Sales / Issue | Screen | Read-only outbound delivery details. | Simple | 0.25 | Iteration 1 | Planned | To Do | danghh | 30/10/26 | To Do | minhtd | 04/11/26 | To Do | minhtd | 06/11/26 | danghh; W8; code 30/10/2026
UC-51 Create Outbound Delivery | FE-06 | Sales / Issue | Screen | Sales plans OD within net WIR allowance; redelivery reuses original OD or traceably transfers reopened commitment to replacement OD without new demand. | Medium | 1 | Iteration 1 | Planned | To Do | danghh | 30/10/26 | To Do | minhtd | 04/11/26 | To Do | minhtd | 06/11/26 | danghh; W9; code 06/11/2026
UC-52 View Picking Task List | FE-06 | Sales / Issue | Screen | Read authorized warehouse picking tasks associated with outbound delivery releases. | Simple | 0.25 | Iteration 1 | Planned | To Do | danghh | 30/10/26 | To Do | minhtd | 04/11/26 | To Do | minhtd | 06/11/26 | danghh; W9; code 06/11/2026
UC-53 View Picking Task Details | FE-06 | Sales / Issue | Screen | Read required lot/location, assigned quantities, reservations, actual picks and shortage/defect evidence. | Simple | 0.25 | Iteration 1 | Planned | To Do | danghh | 30/10/26 | To Do | minhtd | 04/11/26 | To Do | minhtd | 06/11/26 | danghh; W9; code 06/11/2026
UC-54 Create Picking Task | FE-06 | Sales / Issue | Screen | Warehouse creates picking TO against existing draft GI-S/OD, with compatible stock and FIFO within compatibility; task is execution, not Owner approval. | Medium | 1 | Iteration 1 | Planned | To Do | danghh | 30/10/26 | To Do | minhtd | 04/11/26 | To Do | minhtd | 06/11/26 | danghh; W9; code 06/11/2026
UC-55 Confirm Picking Task | FE-06 | Sales / Issue | Screen | Warehouse Staff confirms actual BOX/PIECE quantities into staging and preserves reservations and total stock. Shortage/damage routes to BF-02/05 or replanning; no silent stock correction. | Complex | 1.5 | Iteration 1 | Planned | To Do | danghh | 30/10/26 | To Do | minhtd | 04/11/26 | To Do | minhtd | 06/11/26 | danghh; W9; code 06/11/2026
UC-56 View goods issue list | FE-06 | Sales / Issue | Screen | Search by source request, issue date, and status. | Simple | 0.25 | Iteration 2 | Planned | To Do | danghh | 13/11/26 | To Do | minhtd | 18/11/26 | To Do | minhtd | 20/11/26 | danghh; W10; code 13/11/2026
UC-57 View goods issue details | FE-06 | Sales / Issue | Screen | Display lot, location, prepared quantity, and actual issued quantity by line. | Simple | 0.25 | Iteration 2 | Planned | To Do | danghh | 13/11/26 | To Do | minhtd | 18/11/26 | To Do | minhtd | 20/11/26 | danghh; W10; code 13/11/2026
UC-58 Post Goods Issue | FE-06 | Sales / Issue | Screen | Warehouse creates/updates GI-S draft before picking, then posts actual confirmed handover once. Draft changes no stock; PGI does not itself mean DELIVERED/COMPLETED. | Complex | 1.5 | Iteration 2 | Planned | To Do | danghh | 13/11/26 | To Do | minhtd | 18/11/26 | To Do | minhtd | 20/11/26 | danghh; W10; code 13/11/2026
UC-63 View defective goods list | FE-07 | Defect / Return | Screen | Filter defect cases by source, product/lot/location, ownership, evidence, unresolved quantity and disposition. | Simple | 0.25 | Iteration 1 | Planned | To Do | trungph | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | trungph; W8; code 30/10/2026
UC-64 View defective goods details | FE-07 | Defect / Return | Screen | Show affected quantity, ownership/custody, inspector, evidence, approval and related outcomes; no duplicate deduction across cases. | Simple | 0.25 | Iteration 1 | Planned | To Do | trungph | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | trungph; W8; code 30/10/2026
UC-65 Inspect Defective Goods and Submit Disposition | FE-07 | Defect / Return | Screen | Warehouse immediately blocks suspect stock and records evidence; within B1 freeze record balance-neutral defect_hold without ordinary quality/location posting. | Complex | 1.5 | Iteration 1 | Planned | To Do | trungph | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | trungph; W8; code 30/10/2026
UC-66 Approve or reject defective goods disposition | FE-07 | Defect / Return | Screen | Owner decides scoped destruction/regrade/release outside stocktake; supplier return uses BF-08 without Owner. B1 quality/location approval is UC-92, not duplicate UC-66. | Medium | 1 | Iteration 1 | Planned | To Do | trungph | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | trungph; W8; code 30/10/2026
UC-67 Record approved defective goods disposition | FE-07 | Defect / Return | Screen | Warehouse executes approved destruction/regrade/release outside freeze. Supplier return deducts only at UC-82; B1 quality/location posts only in UC-93 batch. | Complex | 1.5 | Iteration 1 | Planned | To Do | trungph | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | trungph; W9; code 06/11/2026
UC-68 View customer return list | FE-07 | Defect / Return | Screen | Search CR/FD by mode, source, reason and inspection/receipt status. | Simple | 0.25 | Iteration 1 | Planned | To Do | trungph | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | trungph; W9; code 06/11/2026
UC-69 View customer return details | FE-07 | Defect / Return | Screen | Show source, custody/ownership, quantity, physical condition, per-line D6 assessment versions/evidence, proper Sales ordinary/Owner exception decision, FD source/receipt/net reopening and external financial-reference status. | Simple | 0.25 | Iteration 1 | Planned | To Do | trungph | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | trungph; W9; code 06/11/2026
UC-70 Create Customer Return Request | FE-07 | Defect / Return | Screen | Sales creates commercial CR only against customer-received POD or verified historical delivery, with D6 terms and source caps. FD requires no Sales CR and uses Warehouse UC-72/73. | Medium | 1 | Iteration 1 | Planned | To Do | trungph | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | trungph; W9; code 06/11/2026
UC-71 Decide Customer Return Acceptance | FE-07 | Defect / Return | Screen | C2: Sales accepts/rejects ordinary CR after Warehouse inspection, including own creation. Owner only decides eligible exceptions with distinct requester. Neither overrides D6 exclusions; FD bypasses commercial acceptance. | Medium | 1 | Iteration 1 | Planned | To Do | trungph | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | trungph; W9; code 06/11/2026
UC-72 Inspect Return or Failed-Delivery Intake | FE-07 | Defect / Return | Screen | Warehouse distinguishes CR after customer receipt from FD before receipt. CR records customer custody/D6; FD uses posted GI-S/failure evidence and ARR/INS, without D6, fictitious POD, Owner approval or customer custody. | Complex | 1.5 | Iteration 2 | Planned | To Do | trungph | 13/11/26 | To Do | bachhm | 18/11/26 | To Do | bachhm | 20/11/26 | trungph; W10; code 13/11/2026
UC-73 Post Customer Return or Failed-Delivery Receipt | FE-07 | Defect / Return | Screen | Warehouse posts GR-CR under proper Sales ordinary/Owner exception decision; FD posts GR-FD from actual eligible GI-linked receipt without commercial approval, atomically reopening exact original net demand. | Complex | 2 | Iteration 2 | Planned | To Do | trungph | 13/11/26 | To Do | bachhm | 18/11/26 | To Do | bachhm | 20/11/26 | trungph; W10; code 13/11/2026
UC-79 View supplier return request list | FE-07 | Defect / Return | Screen | Search by supplier, lot, reason, agreement and reconciliation status. | Simple | 0.25 | Iteration 2 | Planned | To Do | trungph | 13/11/26 | To Do | bachhm | 18/11/26 | To Do | bachhm | 20/11/26 | trungph; W10; code 13/11/2026
UC-80 View supplier return request details | FE-07 | Defect / Return | Screen | Display lot, location, quantity, source receipt, verified supplier agreement, ACK and Accountant reconciliation outcome. | Simple | 0.25 | Iteration 2 | Planned | To Do | trungph | 13/11/26 | To Do | bachhm | 18/11/26 | To Do | bachhm | 20/11/26 | trungph; W10; code 13/11/2026
UC-81 Create Supplier Return Request | FE-07 | Defect / Return | Screen | Warehouse proposes source-linked SR and isolates defects/reserves good goods. Accountant verifies supplier agreement; there is no Owner dispatch/variance/closure approval. | Medium | 1 | Iteration 2 | Planned | To Do | trungph | 13/11/26 | To Do | bachhm | 18/11/26 | To Do | bachhm | 20/11/26 | trungph; W11; code 20/11/2026
UC-82 Confirm Supplier Return Dispatch | FE-07 | Defect / Return | Screen | Warehouse posts actual GI-SR or supplier-custody release within Accountant-verified agreement/source quantity, without Owner authorization. ACK is a later event. | Complex | 1.5 | Iteration 2 | Planned | To Do | trungph | 13/11/26 | To Do | bachhm | 18/11/26 | To Do | bachhm | 20/11/26 | trungph; W11; code 20/11/2026
UC-83 Review Supplier Return Closure | FE-07 | Defect / Return | Screen | Accountant reconciles and closes accounted supplier-return warehouse quantity under UC-83/107 without Owner. Unresolved disputes stay open; external financial status is independent. | Medium | 1 | Iteration 2 | Planned | To Do | trungph | 13/11/26 | To Do | bachhm | 18/11/26 | To Do | bachhm | 20/11/26 | trungph; W11; code 20/11/2026
UC-84 View stocktake list | FE-08 | Stocktake / Report | Screen | Search stocktakes by warehouse, scope, cutoff time, and status. | Simple | 0.25 | Iteration 1 | Planned | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | bachhm; W8; code 30/10/2026
UC-85 View stocktake details | FE-08 | Stocktake / Report | Screen | View included lots/locations, system snapshot, counted quantities, and variances. | Simple | 0.25 | Iteration 1 | Planned | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | bachhm; W8; code 30/10/2026
UC-86 Create Stocktake Session | FE-08 | Stocktake / Report | Screen | Store Owner plans monthly or targeted stocktakes, scope and counters. Planning does not take a snapshot or post stock; no new automatic scheduling job. | Medium | 0.75 | Iteration 1 | Planned | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | bachhm; W8; code 30/10/2026
UC-87 Perform Stocktake Count and Record Results | FE-08 | Stocktake / Report | Screen | Warehouse activates immutable snapshot/freeze, counts and retains attempts. Defects discovered under B1 produce immediate hold/evidence without balance changes. | Complex | 1.5 | Iteration 1 | Planned | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | bachhm; W9; code 06/11/2026
UC-88 Reconcile Stocktake | FE-08 | Stocktake / Report | Screen | Warehouse compares quantity/quality/location; substantiated variance may proceed directly to plan, while unclear/chosen recount repeats Start/Enter Recount. Quality-only B1 still needs resolution. | Complex | 1.5 | Iteration 1 | Planned | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | bachhm; W9; code 06/11/2026
UC-89 View inventory adjustment request list | FE-08 | Stocktake / Report | Screen | Search by stocktake, lot, location, variance reason, and approval status. | Simple | 0.25 | Iteration 1 | Planned | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | bachhm; W9; code 06/11/2026
UC-90 View inventory adjustment request details | FE-08 | Stocktake / Report | Screen | Display before/after quantities, cause, creator, evidence, and approval decision. | Simple | 0.25 | Iteration 1 | Planned | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | bachhm; W9; code 06/11/2026
UC-91 Create Inventory Adjustment Request | FE-08 | Stocktake / Report | Screen | Warehouse proposes B1 stocktake resolution with actual nonzero total delta and separate total-preserving RECLASS/location lines. Quality-only uses ST_RESOLUTION without ADJ=0. | Complex | 1.5 | Iteration 2 | Planned | To Do | bachhm | 13/11/26 | To Do | trungph | 18/11/26 | To Do | trungph | 20/11/26 | bachhm; W10; code 13/11/2026
UC-92 Approve Stocktake Resolution | FE-08 | Stocktake / Report | Screen | Owner approves/returns versioned B1 plan including actual delta, RECLASS and controlled locations with distinct requester; approval never bypasses freeze or posts stock. | Complex | 1.5 | Iteration 2 | Planned | To Do | bachhm | 13/11/26 | To Do | trungph | 18/11/26 | To Do | trungph | 20/11/26 | bachhm; W10; code 13/11/2026
UC-93 Clear Stocktake Difference | FE-08 | Stocktake / Report | Screen | Owner posts one approved B1 closure batch: actual nonzero delta if any plus total-preserving RECLASS/location, after Warehouse execution. Unlock only resolved scope; no ADJ=0. | Complex | 2 | Iteration 2 | Planned | To Do | bachhm | 13/11/26 | To Do | trungph | 18/11/26 | To Do | trungph | 20/11/26 | bachhm; W11; code 20/11/2026
UC-94 Sign in to the system | FE-09 | Stocktake / Report | Screen | Access authorized functions according to the assigned account and role. | Simple | 0 | Iteration 1 | Coded | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | Existing implementation; regression pending
UC-95 View account list | FE-09 | Stocktake / Report | Screen | Search and filter accounts by name, role, and active status. | Simple | 0 | Iteration 1 | Coded | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | Existing implementation; regression pending
UC-96 View account details | FE-09 | Stocktake / Report | Screen | Display the selected account's information, assigned role, and status. | Simple | 0 | Iteration 1 | Coded | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | Existing implementation; regression pending
UC-97 Maintain Staff Account | FE-09 | Stocktake / Report | Screen | Create, update, activate or deactivate staff accounts; role assignment remains separately controlled. | Simple | 0 | Iteration 1 | Coded | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | Existing implementation; regression pending
UC-98 Assign roles and operation permissions | FE-09 | Stocktake / Report | Screen | Maintain exactly the existing five roles, operation rights and assigned warehouse scope. No purchasing/delivery role, proxy entry or dynamic delegation workflow is introduced. Multiple roles do not permit self-approval. | Simple | 0 | Iteration 1 | Coded | To Do | bachhm | 30/10/26 | To Do | trungph | 04/11/26 | To Do | trungph | 06/11/26 | Existing implementation; regression pending
UC-99 View Operational Reports | FE-09 | Stocktake / Report | Screen | Run authorized physical/available/reserved/custody/transit, outstanding receipt/issue, customer-received quantities, DELIVERED pending receipt, COMPLETED/cancelled orders, defect, transfer, return and stocktake reports; no revenue/profit reports. | Simple | 0.25 | Iteration 2 | Planned | To Do | bachhm | 13/11/26 | To Do | trungph | 18/11/26 | To Do | trungph | 20/11/26 | bachhm; W11; code 20/11/2026
UC-100 View stock movement log | FE-09 | Movement / Transfer | Screen | Filter movements by product, lot, location, transaction type, and time. | Simple | 0.25 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W8; code 30/10/2026
UC-101 View stock movement details | FE-09 | Movement / Transfer | Screen | Display source document, before/after quantity, operator, time, and reason. | Simple | 0.25 | Iteration 1 | Planned | To Do | hieudt | 30/10/26 | To Do | bachhm | 04/11/26 | To Do | bachhm | 06/11/26 | hieudt; W8; code 30/10/2026
UC-102 Trace a product lot through source documents | FE-09 | Defect / Return | Screen | Trace lots across external source → SO → WIR → OD → GI-S → POD → PAY-CFM and linked receipts, reservations, movements, returns and adjustments with evidence and user/time history. | Simple | 0.25 | Iteration 2 | Planned | To Do | trungph | 13/11/26 | To Do | bachhm | 18/11/26 | To Do | bachhm | 20/11/26 | trungph; W11; code 20/11/2026
UC-103 View and Select Shortage Fulfilment Options | FE-06 | Sales / Issue | Screen | Sales/Warehouse compares compatible available stock by warehouse and selects direct dispatch, physical transfer or replenishment. Link BF-01/04/06; suggestions do not automatically order or post. | Medium | 1 | Iteration 2 | Planned | To Do | danghh | 13/11/26 | To Do | minhtd | 18/11/26 | To Do | minhtd | 20/11/26 | danghh; W10; code 13/11/2026
UC-104 Inspect and Post Transfer Receipt | FE-05 | Movement / Transfer | Screen | Destination Warehouse Staff independently verifies actual quantities against dispatch lines and posts MWTR by quality. Move received quantities from transit to destination, retain demand allocation, put away and keep discrepancies open. | Complex | 1.5 | Iteration 2 | Planned | To Do | hieudt | 13/11/26 | To Do | bachhm | 18/11/26 | To Do | bachhm | 20/11/26 | hieudt; W11; code 20/11/2026
UC-105 Export or Print Stocktake Count Sheet | FE-08 | Stocktake / Report | Screen | Warehouse Staff/Owner obtains the activated session's snapshot-based list by location/lot/quality, with cutoff and space for counts and newly found items. Printing does not post stock. | Medium | 1 | Iteration 3 | Planned | To Do | bachhm | 25/11/26 | To Do | trungph | 25/11/26 | To Do | trungph | 27/11/26 | bachhm; W12; code 27/11/2026
UC-107 Record Supplier Agreement and Receipt Acknowledgement | FE-07 | Defect / Return | Screen | Accountant verifies pre-dispatch agreement and separately records later ACK, reconciles variances and closes through UC-83 without Owner/UC-106. | Medium | 1 | Iteration 3 | Planned | To Do | trungph | 25/11/26 | To Do | bachhm | 25/11/26 | To Do | bachhm | 27/11/26 | trungph; W12; code 27/11/2026
UC-108 Record External Document References | FE-09 | Defect / Return | Screen | Accountant verifies historical delivered sources and records external Invoice/Credit Note/refund/reconciliation kind, number/date, purchase/GI-SR source, matched quantity, evidence and status independently of warehouse closure. | Medium | 1 | Iteration 3 | Planned | To Do | trungph | 25/11/26 | To Do | bachhm | 25/11/26 | To Do | bachhm | 27/11/26 | trungph; W12; code 27/11/2026
UC-109 Manage Linked Warehouse Issue Request | FE-06 | Sales / Issue | Screen | Sales manages original SO-linked WIR and net reopened demand after posted GR-FD. Reuse original SO/WIR and source versions; replacement OD commitment is transferred, not new demand. | Complex | 1.5 | Iteration 2 | Planned | To Do | danghh | 13/11/26 | To Do | minhtd | 18/11/26 | To Do | minhtd | 20/11/26 | danghh; W11; code 20/11/2026
UC-110 Confirm Customer Delivery with Photo Evidence | FE-06 | Sales / Issue | Screen | Assigned Warehouse confirms actual customer receipt against valid posted GI-S with photo. Share source cap with FD/GR-FD; received quantity uses CR for later return. | Medium | 1 | Iteration 2 | Planned | To Do | danghh | 13/11/26 | To Do | minhtd | 18/11/26 | To Do | minhtd | 20/11/26 | danghh; W11; code 20/11/2026
UC-111 Confirm Full External Payment Receipt | FE-06 | Sales / Issue | Screen | Only Sales confirms full money receipt outside WMSD after rechecking current-version DELIVERED. Reference/evidence/note and user/time are required; atomically set COMPLETED without stock or payment execution. | Medium | 1 | Iteration 2 | Planned | To Do | danghh | 13/11/26 | To Do | minhtd | 18/11/26 | To Do | minhtd | 20/11/26 | danghh; W11; code 20/11/2026
(*) You can rate the functions' complexity level based on the number of fields on the screens or the number of transactions in the function, with the details as below
Simple | <=7 fields | <=3 transactions
Medium | <=15 fields | <= 7 transactions |  |  |  | Planned | Functions | Total Effort
Complex | >15 fields | > 7 transactions |  |  |  | Iteration 1 | 63 | 33.75
In which: | [5 empty] | Iteration 2 | 31 | 30.5
fields: screen components or database table fields | [5 empty] | Iteration 3 | 3 | 3
transactions can be counted actioning UI components, user or database access transactions | [5 empty] | Grand Total | 97 | 67.25
Note on G1: kiennt: Estimated for Coding & Unit-Testing Effort, in man-days

## Q&A
Date | Question | By | Priority | Due Date | Status | Note (answer, other notes)
2023-09-16 |  | KienNT | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open
|  |  | Medium |  | Open

## Issues
Date | Issue | Priority | Created | Owner | Due Date | Status | Notes
2024-10-13 |  | Medium | KienNT | HuyNMG |  | Open
|  | Medium |  | HuyNMG |  | Open
|  | Medium |  | HuyNG |  | Open
|  | Medium |  | HuyNG |  | Open
|  | Medium |  | HuyNG |  | Open
|  | Medium |  | DucBH |  | Open
|  | Medium |  | HuyLQ |  | Open

## Defects
Date | Defect Description | Activity | Product | Product Details | Assigner | Assignee | Status | Updated | Notes
2024-10-13 |  | Review | Software Package |  |  |  | Pending | 2024-10-26
|  | Review | Report1 (Intro) |  |  |  | Pending
|  | Review | Report4 (SDS) |  |  |  | Pending
|  | Review | Report4 (SDS) |  |  |  | Pending
|  | Review | Report5 (Test) |  |  |  | Pending
|  | Review | Report6 (Guides) |  |  |  | Pending
|  | Review | Report4 (SDS) |  |  |  | Pending
|  | Review | Report4 (SDS) |  |  |  | Pending
|  | Review | Report5 (Test) |  |  |  | Pending
|  | Review | Report6 (Guides) |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending
|  | Review | Software/System |  |  |  | Pending
Note on E1: Name of screen, function or the document section